### 🧾 CLIENT BRIEF

Client Name: Finvero
 Industry: Financial Technology (FinTech)
 Startup Stage: Seed-funded, pre-launch
 Services Offered: AI-driven personal finance assistant for Gen Z and Millennials

### 🔍 PROJECT OVERVIEW

Objective:
 We’re building Finvero—a smart finance app that helps users automatically budget, save, and invest using AI. We're seeking a complete brand identity package that reflects our vision: modern, friendly, and trustworthy, while standing out in the often cold and corporate fintech space.

### 🧩 PROJECT SCOPE

You are tasked with creating a comprehensive brand identity package including:

#### 1. Logo Design

- Primary logo (horizontal + stacked versions)

- Wordmark and icon variant

- Dark and light variations

#### 2. Color Palette

- Primary: Fresh, tech-forward tones (we’re open to blues, greens, or purples)

- Secondary: Supporting tones for digital, print, and mobile

#### 3. Typography

- Headline type: Clean, modern sans-serif

- Body copy: Legible, mobile-friendly typeface

- Display or accent font for marketing

#### 4. Brand Voice & Tone

- Friendly, empowering, tech-savvy

- Less corporate, more conversational

- Messaging examples: taglines, onboarding copy, social snippets

#### 5. Stationery & Marketing

- Business card layout

- App icon

- Email signature

- Pitch deck cover template

- Instagram/social media post templates

#### 6. UI Starter Kit (Bonus)

- App splash screen

- Simple homepage wireframe

- CTA button styles

### 📈 BUSINESS GOALS

- Differentiate Finvero from traditional finance apps

- Build early trust with a young user base

- Establish a digital-first brand ready for social, web, and mobile

- Appeal to tech-savvy users and early adopters

### 🕓 TIMELINE & MILESTONES

- Phase 1: Discovery & Moodboard – 1 week

- Phase 2: Logo & Core Brand Assets – 2 weeks

- Phase 3: Style Guide & Templates – 1 week

- Phase 4 (Optional): UI Starter Kit – 1 week

🗓 Total Time: ~4–5 weeks

### 💵 BUDGET

Total: $3,200
 Breakdown:

- Branding & Logo: $1,500

- Style Guide & Templates: $1,000

- UI Starter Kit: $700 (optional, can be added on later)

### 📁 ASSETS PROVIDED TO DESIGNER

- PDF: Founder's pitch deck & business strategy

- Existing competitor analysis & gap matrix

- Early sketches from founder

- Tone of voice document (core phrases & vision)

- A short survey of our early testers

- Brand inspiration Pinterest board (optional)